Annex 4

DAP Activities – Tentative Calendar and Estimated Duration

| Activity | Responsibility/ participants | Duration* | Estimated schedule** |
| --- | --- | --- | --- |
| Issue DAP RFP | UN Purchasing Unit |  | Mid March 2003 |
| Proposals due | Vendor | 30 days | End April |
| Vendor evaluation and selection | UNPO vendor selection team | 30 days | May/June |
| Contract negotiations and award | UN Procurement and Legal | 20 days | June/July |
| Initial meeting with DAP Project Manager | Vendor, PM | 5 days | Mid July |
| Vendor completes Deliverable 1- Proj Management Workplan | Vendor, PM | 10 days | 10 days after initial meeting with DAP PM – End July |
| Vendor completes Deliverable 2 - Digital Assessment – Policy and Proc. | Vendor, PM, WGARM, IT, Programme, Business staff | 25 days | 25 Days after Deliverable 1 is complete*** |
| Vendor completes Deliverable 3 - Digital Assessment – Technical | Vendor, PM, IT, WGARM | 25 days | 25 Days after Deliverable 2 is complete*** |
| Vendor completes Deliverable 4 – DAP Specifications and Requirements | Vendor, PM, IT, WGARM | 60 days | 60 Days after Deliverable 3 is complete*** |
| Vendor completes Deliverable 5 - Implementation Plan | Vendor, PM, WGARM | 50 days | 50 Days after Deliverable 4 is complete*** (Mid January 2004) |
| Vendor completes Deliverable 6 - Marketing and presentations | Vendor, PM, WGARM | 10 days | 10 Days after Deliverable 5 is complete*** |
| Vendor completes Deliverable 7 - WorkPlan Phase II | Vendor, PM, IT, WGARM | 30 days | 30 Days after Deliverable 6 is complete*** ( end February 2004) |
| Phase I complete |  |  | March 2004 |

* Business days

** To be confirmed within Work Plan

*** Estimated schedule assumes that some deliverables will run concurrently with other deliverables