- Ref: UN/CS/RAI/USAA/DB01/2004-00114

- Annex C (DAP Contract) – Project Plan and Schedule

- United Nations Participating Organisations

- Strategic Plan for Digital Archives Programme Project

- Work Plan

- TABLE OF CONTENTS

| - 1.0 Overview | - Page 3 |
| --- | --- |
| - 2.0 Objectives | - Page 3 |
| - 3.0 Project Scope | - Page 4 |
| - 4.0 Project Management Infrastructure - 4.1 Project Procedures - 4.2 Project Analysis - 4.3 Protocols and Report Structures - 4.4 Delivery and Requirements - 4.5 Project Methodology | - Page 4 |
| - 5.0 Milestones/Activities | - Page 5 |
| - 6.0 Deliverables - 6.1 Delivery Acceptance Criteria - 6.2 Major Deliverables (See DAP SOW Section 5) | - Page 6 |
| - DAP Communication Strategies - Communication Protocols - Data Management Tool | - Page 6 |
| - 8.0 Change Management | - Page 7 |
| - Risk Assessment - Risk Issues - Risk Ongoing Analysis | - Page 8 |
| - Timeline | - Page 9 |
| - Resource Requirements | - Page 9 |

- Annex

- Attachment A – Delivery Acceptance Document (DAD)

- Attachment B – Project Request Change Form

- Attachment C – Project Gantt Chart

- United Nations Participating Organisations

- Digital Archives Programme Project

- Work Plan

- 1.0	Overview

Records are defined as all material “regardless of physical form, created or received in connection with or as a result of the official work” and constitute the business, legal, and historical informational assets of the organisation. Although records of all types must be managed and preserved, only recently have the challenges concerning electronic records been recognised.

This project stems from the United Nations Participating Organisations (UNPOs) commitment to build capacity within their archives and records programmes to preserve and make available those knowledge assets of long-term value that are created, converted, and maintained in digital form in a reliable and readily available authorized source.

The Digital Archives Programme (DAP) will provide both a tactical and strategic roadmap for the United Nations Working Group on Archives and Records Management (WGARM) and five participating organizations, UNFPA, UNDP, UNICEF, UNOPS, and UN Secretariat, to develop and apply standards, processes, and procedures for the identification, management, and preservation of electronic records.

Entium Technology Partners’ (Entium) objective is to work with WGARM and DAP Coordinators (selected from each of the five participating organisations) to develop a Strategic Digital Archives Plan that supports the implementation of standardised processes and tools to manage and preserve electronic records. This project will result in a combination of policies, procedures, standards, and technology recommendations that will facilitate the proper management, disposition, and preservation of digital records and provide for the long-term access and use of materials with archival value.

This work plan covers the first of two phases to design and implement a DAP within the UNPOs. This first phase will identify requirements and specifications, define standards, and establish a plan for the implementation of a DAP within the UNPOs. Phase two, which will be the subject for a separate project, will implement the framework and begin the necessary technical and operational activities to develop digital archiving.

2.0	Objectives

The objectives of the DAP are to:

      - Establish guidelines, policies, and standards related to digital records practices.

      - Establish minimal standards, requirements, and specifications for software and network related to digital records technology.

      - Create an implemental framework that can be applied by the UNPOs to establish or to share in the use of digital archives facilities

      - Identify appropriate electronic records management, document management, and digital preservation strategies.

      - Ensure long-term preservation, maintenance, and access to digital records of archival value.

      - Establish good recordkeeping practices.

Projects resulting in process change are unique undertakings, involving a degree of outcome uncertainty. As a result, meeting the UNPOs needs and expectations involve balancing competing demands and addressing key objectives, such as:

      - Standard processes and techniques applied consistently throughout the project life cycle and across the five UNPOs. This will be the model for future DAP implementation throughout the United Nations.

      - Establish and maintain management controls and procedures to ensure timely execution of programme tasks demonstrating progress that define expectations.

      - Adequate funding for all project phases and other initiatives to maintain focus and buy-in of the programme strategic plan.

3.0	Project Scope

The focus of the Strategic Digital Archives Plan is records created or received in the New York UNPOs offices. However, the plan will also identity any issues concerning the preservation and management of digital records created or received in UNPOs offices outside New York if they are integrally related to business processes or operational performance. The major issues related to records created or received in other locations not addressed by the scope of the plan should be noted and potential additional estimated costs identified if the project size were increased to cover other UNPOs locations.

- 4.0	Project Management Infrastructure

Entium will perform a series of tasks with the DAP Project Manager to mutually establish a project management infrastructure. All tasks will be documented as part of the overall work plan so that the project management infrastructure can be closely monitored and adjusted, if necessary.  Entium’s project management methodology is organised into four key tasks defined in the following subsections.

4.1	Project Procedures

Entium will work with the DAP Project Manager to mutually develop procedures to change or modify the workplan and to manage escalating risks and issues. Entium will work with the DAP Project Manager to mutually develop procedures to ensure adherence to the specified standards of practice, manage escalating risks and issues, and, if necessary, modify this work plan.

4.2	Project Analysis

Further analyse and develop the specific work plan so that the UNPOs expectations are fulfilled in a satisfactory manner. The work plan is developed with the technical approach, high-level estimates, resources, and infrastructure required to conduct the project. Project objectives are described and documented in the work plan along with a project schedule and resource requirements, to complete all tasks.  Key tasks during this stage include:

- solidify a timetable for performing the project activities

- identify milestones and resource requirements

4.3	Protocols and Report Structures

Develop a series of comprehensive reports, requirements and specifications, and an implementation plan, which addresses all tasks related to the development of a Strategic Digital Archives Plan. This will be reviewed with the DAP Project Manager and WGARM prior to project schedule finalisation. Data and information will be gathered through interviews with key UNPOs staff and through available written materials and manuals relating to the creation, registration, indexing requirements, and ultimate preservation of long-term digital records.

4.4	Delivery and Support Requirements.

This section will address the execution of the project and acceptance of deliverables. During the initial development of the work plan with the DAP Project Manager, a Deliverable Acceptance Document (DAD) will be established (see annex A). This document, prepared during the execution of the project, will be submitted with each deliverable for the DAP Project Manger’s review and acceptance.

4.5	Project Methodology

The strategic plan is comprised of three principal elements defined in the following subsections.

4.5.1	The assessment and analysis of current digital record functionality within the UNPOs including business context in which records are created, the general recordkeeping requirements, and the capabilities (existing policy, practice, and technology) relating to the identification and preservation of digital records.

4.5.2	The design a DAP framework that includes a comprehensive set of DAP standards, specifications, and requirements as well as identify appropriate electronic records management, document management, and digital preservation strategies, and make proposals of models.

4.5.3	The description within the implementation plan of a high level approach linking the current technical and administrative infrastructure to the DAP. The plan must be scaleable and include maintenance strategies.

5.0	Milestones/Activities

To accomplish our objectives, the following milestones and associated tasks have been identified.

  - Activity  1-7  (see DAP SOW Section 5 for details)

- Activity 1  Establish Project Management Infrastructure

- Activity 2  Survey and review the current policies, procedures, approaches, initiatives and best practices related to digital records

- Activity 3: Inventory the current Information Management data bases and technical platforms related to digital records

- Activity 4  Develop DAP specifications, requirements and standards

- Activity 5  Prepare an Implementation Plan for DAP

- Activity 6  Prepare and Market the DAP Strategic Plan and Implementation Plan

- Activity 7  Prepare a Work Plan for implementation (Phase 2)

6.0      Deliverables

6.1	Delivery Acceptance Criteria

During the initial development of the work plan, Entium will work with the DAP Project Manager to mutual establish a Deliverable Acceptance Criteria document (see Attachment A). This document will be submitted with each deliverable for the DAP Project Manager’s review and acceptance.

6.2	Major Deliverables (see DAP SOW Section 5 for details)

During the development of the milestones described in Section 2, WGARM will be requested to review, edit, and accept the following major deliverables:

    - The Project Work Plan

      - The Digital Records Analysis Report.

      - The Information Systems Technical Characteristics Report.

      - The DAP Specifications, Requirements, and Standards Report.

      - The DAP Implementation Plan.

      - The DAP Marketing and Presentation Materials.

      - The DAP Phase II Work Plan.

- DAP Communication Strategies

  - Communication Protocols

Effective communication protocols not only provide for efficient transfer of knowledge but ensure that the project is on track in terms of deliverable timelines and budget. Additionally, the project stakeholders and impacted personnel are engaged in the process resulting in plan recommendation acceptance. Communication protocols include:

      - Weekly project status reports outlining work accomplished and work planned including issues and concerns.

      - Formal presentations of deliverables and recommendations to WGARM and designated participants.

      - Strategic Digital Archives Plan marketing to all UNPOs.

- To ensure transparency and participation within the UNPOs, each organization will designate a DAP Coordinator, DAP CO, to liase with DAP Project Manager, UNPO staff and Entium Technologies.   As appropriate, DAP Focal Points within each UNPO department will also be designated to liase with departmental staff and the DAP CO.

7.2  	Data Management Tool

The specific tool for collecting draft, work-in-process, and final documents during the course of the project and subsequent phases has yet to be determined. Various solutions are currently being evaluated and will be communicated to the project team prior to the commencement of interviews described in Activity 2.

- Change Management (see DAP Contract for additional details)

Managing project scope changes is critical to ensure the DAP goals are achieved and that the programme success is assured. Entium will use the Project Request Change Form (see Attachment B) to document any project scope changes.

Any request by either Party for a change in the scope of the Project or in the nature of any Deliverables or Services must be made in writing and in a Project Change Request (“PCR”) form, as set forth in Annex B.  The PCR shall, at a minimum specify:

  - the nature of the proposed change in the scope of the Project or the nature of any Deliverables or Services for each step and each task set forth in the Project Plan and Schedule;

  - the reason for the proposed change in the scope of the Project or the nature of any Deliverables or Services;

  - the estimated impact, if any, of the proposed change in the scope of the Project or the nature of any Deliverables or Services; and,

  - The estimated impact, if any, on the prices to be paid for the Deliverables and Services in accordance with this Contract.

An example of a Project Scope change includes:

- If the project is expanded to other locations outside of New York City, this would constitute a change in scope and Entium would submit a Project Request Change Form.

9.0	Risk Assessment

The success of a project of this magnitude, when addressing process change for employees creating, indexing, accessing, distributing, retaining, and preserving digital records, has specific risks that need to be addressed throughout the life cycle of the project.

9.1	Risk Issues

Risks that are identified that may impact the success of this project are:

    - UNPOs unwillingness to integrate, link or alter existing or planned technology tools since specifications will not be available until mid 2005.

    - UNPOs’ culture of decentralisation may not respond to a plan that may recommend centralised solutions.

    - End-user expectations versus participating organisations’ budget and resource constraints.

    - ‘Information ownership’ issues concerning information sharing and collaboration.

    - Avoidance of standards and sharing common approach in managing digital records will result in inconsistent preservation, identification, and management of digital records.

    - Not implementing a DAP will result in local initiatives subject to the inconsistent applications and changes in management.

  - Risk Ongoing Analysis

As the project progresses from interviews and collected data, additional risks identified by level of severity include:

    - Technology failure caused by natural and/or man-caused disasters: (LOW).

As with inadequate record keeping practices, the use of digital tools to conduct business without the appropriate level of backup and security is courting disaster.

    - Risks associated with not implementing a DAP: (MEDIUM).

Although the UNPOs have generated various studies, guidelines, reports, and executive statements since the mid 1980s, little has been done towards implementing an agency-wide programme.

    - Risk related to budget constraints: (MEDIUM).

While it is hoped that monies have been allocated to both develop and implement a Strategic Digital Archives Plan, the demand on budget can often shift toward other perceived priorities, the implementation timeline can slip, or the need for such programmes simply not adequately recognised.

    - Risk due to delayed or limited management support: (HIGH).

While there is a potential for records programmes to be pushed to the background while other issues demand attention, the experience and quality of our project team and project manager will strive to minimize this risk.

    - Risk of different technologies: (HIGH).

It is known that the UNPOs currently use a variety of technology tools to conduct their daily business transactions. The DAP will have components that must interact with records throughout their life cycle despite these differences.

10.0	Timeline

The project is commenced August 18, 2004 and target completion by the end of May, 2005. Specific activity timelines are:

    - Activity 1 – Project Work Plan Development Tasks (Aug. 18 through Oct. 6, 2004).

    - Activity 2 – Survey Digital Records Practices Tasks (Sept. 23 through Dec. 8, 2004).

    - Activity 3 – Collect Information Systems Tasks (Oct. 27, 2004 through Jan. 4, 2005).

    - Activity 4 – DAP Specification Tasks (Jan. 5 through Feb. 28, 2005).

    - Activity 5 – DAP Implementation Plan Tasks (Mar. 1 through Mar 23, 2005).

    - Activity 6 – Communicate and Market DAP Tasks (Mar. 28 through Apr. 28, 2005).

    - Activity 7 – DAP Implementation Work Plan Tasks (Apr. 29 through May 19, 2005).

Please refer to Attachment C, Project Gantt Chart, for details pertaining to resources assigned to each task and their specified duration.

11.0	Resources Requirements

The following resources will be applied during the project to perform the activities and tasks noted in this work plan:

Entium Resources

| Name | Project Position | Activity Responsibility | Level of Effort |
| --- | --- | --- | --- |
| Fred V. Diers | Project Manager | Activities 1 through 7 | 140 hours |
| Christine Ardern | Process Consultant | Activities 2, 4, 5, & 6 | 420 hours |
| Robert Turner | Technology Consultant | Activities 3, 4, 5, & 6 | 335 hours |
| Jim Mernin | Technology Consultant | Activities 3, 4, 5, & 6 | 100 hours |
| Sean Rickert | Inventory Consultant | Activities 2, 3, 4, 5, & 6 | 400 hours |

UNPOs Resources

| Name | Project Position | Activity Responsibility | Level of Effort |
| --- | --- | --- | --- |
| Dhurjati Mueller | Project Manager | Activities 1 through 7 | 280 hours |
| WGARM | Stakeholders | Deliverable Acceptance | 256 hours |
| DAP Coordinators | UNPOs Representatives | Activities 3 & 4 | As Needed |
| UNPOs Focal Points | Interviewees | Activities 3 & 4 | As Needed |
| UNPOs Personnel | Data Input/Interviewees | Activities 3 & 4 | As Needed |