UN-CS-RAI-USAA-DB01-2005-00055

Weekly Project Status Report

United Nations Participating Organisations

Strategic Plan for Digital Archives Program

| For: United Nations Participating Organisations – Dhurjati Mueller | From: Entium Technology Partners LLC - Fred Diers, CRM, FAI Principal, Records and Information Management 610-415-7227, fdiers@entium.com |
| --- | --- |
| ## For the week ending February 19, 2005 |  |
| Tasks Completed by F. Diers (Entium Project Manager): - Prepared and issued project status report. Tasks Completed by Entium Project Team: - Robert Turner and Christine Ardern participated in Business Unit interviews on Tuesday and Wednesday. - Wednesday afternoon the UN project team, Robert Turner, and Christine Ardern discussed the projects status and concluded that: - Draft report for Deliverable 2 and Deliverable 3 will be separated. - Business Unit interviews will be concluded by the week of March 8th. - Deliverable 2 report will be submitted to the UN after Business Unit interviews have concluded and the questionnaires have been returned and the analysis completed. - Deliverable 3 report will be submitted to the UN next week - Deliverable 4 reports are being developed now and will be submitted to the UN at the end of March. - Records sampling has been included in the Business Unit questionnaires and will not be considered a separate activity in deliverable 2. Data collected will be part of the BU questionnaire. |  |
| Tasks to be Accomplished the week beginning February 21, 2005 - Participate in Business Unit Interviews scheduled for Thursday and Friday in New York. . - Submit report on Deliverable 3 to Dhurjati and process Entium invoice. - Robert Turner will submit draft meeting minutes from Wednesday’s meeting to Dhurjati by next Tuesday - Submit revised draft report of Deliverable 2 to Dhurjati for review based on updated format by end of week. |  |
| Project Action Items (including issues and concerns): - Continue developing the Draft DAP implementation plan for deliverable 4 and review possible models for submittal to Dhurjati. - Upcoming objectives are: - Complete Deliverable 3 by next week - Complete Deliverable 2 by mid March - Complete Deliverable 4 by end of March |  |