UN-CS-RAI-USAA-DB01-2005-00076

Weekly Project Status Report

United Nations Participating Organisations

Strategic Plan for Digital Archives Program

| For: United Nations Participating Organisations – Dhurjati Mueller | From: Entium Technology Partners LLC - Fred Diers, CRM, FAI Principal, Records and Information Management 610-415-7227, fdiers@entium.com |
| --- | --- |
| ## For the week ending March 5, 2005 |  |
| Tasks Completed by F. Diers (Entium Project Manager): - Prepared and issued project status report. Tasks Completed by Entium Project Team: - Robert Turner and Christine Ardern finalized the deliverable 3 report to be reviewed by WGARM members. - Prepared for next weeks Business Unit interviews. - Started developing the spreadsheet for Business Unit interview summaries. - Continue to develop deliverable 2 and 4 reports |  |
| Tasks to be Accomplished the week beginning March 7, 2005 - Christine Ardern and Robert Turner will participate in UN Business Unit interviews Tuesday, Wednesday, and Thursday. - Prepare Business Unit interview notes. - Continue working on Deliverable 2 and 4 reports. |  |
| Project Action Items (including issues and concerns): - Continue developing the Draft DAP implementation plan for deliverable 4 and review possible models for submittal to Dhurjati. - Upcoming objectives are: - Complete draft of deliverable 2 during March. - Complete draft of deliverable 4 by end of March. |  |