COMMON SERVICES PROJECT

1999 SUMMARY WORKPLAN

Working Group for Archives and Records Management

| WORK ACTIVITY |  | JAN 1 | FEB 2 | MAR 3 | APR 4 | MAY 5 | JUN 6 | JUL 7 | AUG 8 | SEP 9 | OCT 10 | NOV 11 | DEC 12 | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Receive OLA Advice on Implications for using Archiving Services/Record Storage of Private Sector or Host country |  | X |  |  |  |  |  |  |  |  |  |  |  | Has implications for Move of UN Archives and for CS/Research Centre |
| Finalization of UN Archives Location for Move 2000. Identify all major tasks to be completed or budgeted by end 1999 |  |  | X |  |  |  |  |  |  |  |  |  |  | Need Sufficient time for budgeting, designing site, evaluating collection risks and move |
| Working Relationship with ISCC/SIGs to be regularized |  |  |  | X |  |  |  |  |  |  |  |  |  | Possible Joint efforts with other locations for Workplan items |
| Final Plan on use Common Service Archive Research Centre [CS/ARM] by other UN organizations for Core Records |  |  |  |  |  |  | X |  |  |  |  |  |  | Test obtaining funding from External Sources: foundations etc. Consider securing consultant |
| WG propose Items to Be available on common Web site |  |  |  |  |  |  |  |  |  |  |  | X |  | Policy, Procedure and Guidelines |
| Joint Agency review of Advice to Field Offices & Modules for Common Workbook |  |  |  |  |  |  |  |  |  |  |  | X |  | Adapt UNICEF & UN materials. Consider Joint SSA to extend |
| Review Status of Digital Archives plan for UN organizations |  |  |  |  |  |  |  |  |  |  | X |  |  | Organizations comment on UN/ARMS plan for Phase 1 of Study |
| Plan for Appraisal Decision Assistance Project and Funding |  |  |  |  |  |  |  |  |  |  |  |  | X | Identify candidate tools and begin collecting rules |
| WORK ACTIVITY |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC |  |

General Notes: