COMMON SERVICES PROJECT

1999 SUMMARY WORKPLAN

Working Group for Archives and Records Management        [UN/CS/ARM/1999-015]

| WORK ACTIVITY |  | JAN 1 | FEB 2 | MAR 3 | APR 4 | MAY 5 | JUN 6 | JUL 7 | AUG 8 | SEP 9 | OCT 10 | NOV 11 | DEC 12 | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Receive OLA Advice on Implications for using Archiving Services/Record Storage of Private Sector or Host countries |  | 0 |  |  | Rev X |  |  |  |  |  |  |  |  | Has implications for Move of UN Archives, use of national or local service/facility and CS/Arc Research Centre |
| Finalisation of UN Archives Location for Move 2000. Identify all major tasks to be completed or budgeted by end 1999 |  |  | 0 |  |  |  |  |  |  | # Rev ## X |  |  |  | Need Sufficient time for budgeting, designing site, evaluating collection risks and move |
| Working Relationship with ISCC/SIGs to be regularised |  |  |  | 0 |  |  |  |  |  |  |  | rev X |  | Awaiting clarifications from ISCC, Possible Joint efforts with other locations for Workplan items. on hold – other priorities *note 2 |
| WG propose Items to Be available on common Web site |  |  |  |  |  |  |  |  |  |  |  | 0 | Rev Jan 2000 | Joint Agency Special project on Policy, Procedure and Guidelines on hold due to funding. |
| Joint Agency review of Advice to Field Offices & Modules for Common Workbook |  |  |  |  |  |  |  |  |  |  |  | 0 | Rev X | Review UNICEF, UN and UNOPS 1999 developed materials. Consider Joint SSA to extend during 2000 |
| Review Status of a Digital Archives: plan for UN organisations |  |  |  |  |  |  |  |  |  |  | 0 |  | Rev Feb 2000 | Organisations comment on UN/ARMS prepared plan for Phase 1 of Study |
| Final Plan on use Common Service Archive Research Centre [CS/ARM] approach by UN and other organisations for Core Records |  |  |  |  |  |  | 0 |  |  |  |  |  | Rev May 2000 | On hold till 2000 Test obtaining funding from External Sources: foundations etc. Consider securing consultants: See note 3 below |
| Plan for Appraisal Decision Assistance Project and Funding |  |  |  |  |  |  |  |  |  |  |  |  | 0 Rev Jul 2000 | Identify candidate software tools, begin collecting appraisal rules, note possible interest/ support/ partnership of academic or cultural community |
| Address need for External funding and requirement of clear guidelines for partnerships from Common Service Task Force or legal advisors |  |  |  |  |  |  |  |  |  |  |  |  | Apr 2000 | Explore External funding options for WG/ARM identified 19 related functions and Services |
| Review all previously submitted Special ARM related projects in light of funding options and guidelines: |  |  |  |  |  |  |  |  |  |  |  |  | Jun 2000 | Adjust all action plans after securing lead agency agreement for specific project e.g. Declassification Review. |
| WORK ACTIVITY |  | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC |  |

General Notes:

## For chart:  0 = previously proposed, Rev X = now proposed.

## WG/ARM  members  expressed concern that they are over committed for 1999  [e.g. UN Archives & UNOPS move, UNICEF migration from legacy RAMP/WANG system & roll out of new RAMP/TRIM system]

## CS/ARC: On hold - WG/ARM  possibly review again by Q2 2000. Consider joint consultant[s] to expedite funding for long-term and highly valuable core records/services. Include increased access for partners and interested academic institutions as goal. Need to assure sustainable participating agency commitment to encourage external support.

Would need to Decide on consultant[s] to:

-  Refine CS/ARC package/ presentation for various audiences.

-  Develop approved funding strategy and approach contributors/ donors

-   Draft agreements on  Services and costs to be shared