1. WG - Archives & Records Management:   [UN/CS/ARM/1999-016]

General Considerations:

WG Agreements:

- Establish a Coordinating Committee on Archives & Records Management

- Establish an CS Archives Research Centre

- Develop & implement a common strategy for long-term preservation & retrievability of electronic records

| Deliverables as of December 1998 | Target Date | Implementation Status March 1999 |  | New Deliverables as of March 1999 | New Target Date |
| --- | --- | --- | --- | --- | --- |
| 1. Finalisation of UN Archives location. | Feb. 1999 | Awaiting OLA input on implications of external contracting for UN records or archives. |  | Expected OLA feedback | April 1999 |
| 2. Working relationship with ISCC (+SIGs) to be regularised | March 1999 | On hold pending ISCC clarification and other NY priorities*. |  |  | Oct 1999 |
| 3. Final plan on common use of UN Archives by other organisations for core long term Records | May 1999 | Current shared holdings [UNFPA & UNICEF] to be addressed during UN ARM move discussions. |  | Agree Plan for shared holdings impacted by UN ARM move. [CS/ARM] on hold see item 7, | Nov 1999 |
| 4. WG proposes items to be available on common website | Nov. 1999 | Ongoing – funding for special project on hold. |  | Joint agency project on harmonisation of Archives and Records policies and procedures | Jan 2000 |
| 5. Digital Archives Study, Phase one Review | Sept 1999 | Consultant report presented, next phases on hold – budget constraints |  | Members to comment on study implications for CS approach to security of electronic records for 2001-2003 | Feb 2000 |
| 6. External funding |  | Need for external funding noted. Clear guidelines required. |  | Explore External funding options for WG/Arm identified 19 related functions and Services | Apr 2000 |
| 7. Common Service/ Archive Research Center or approach |  | On hold - WG/ARM possibly review again by Q2 2000. Consider joint consultant[s] to expedite funding for long-term and highly valuable core records/services. Include increased access for partners and interested academic institutions as goal. Need to assure sustainable participating agency commitment to encourage external support. |  | Decide on consultant[s] to: - Refine CS/ARC package/ presentation for various audiences. - Develop approved funding strategy and approach contributors/ donors - Draft agreements on Services and costs to be shared | May 2000 |
| 8. Special projects review |  | Other proposed special projects on hold |  | Review all previously proposed special projects in light of funding options: e.g. Declassification Review, Appraisal Decision Assistance. Adjust action plans. | Jun 2000 |
| Note :WG/ARM members expressed concern that they are over committed for 1999 [e.g. UN Archives & UNOPS move, UNICEF migration from legacy system & roll out of new system] |  |  |  |  |  |

WG Chairperson(s):

Ms. Marilla Guptil , UN/OCSS

Mr. Adhiratha Kevin Keefe, UNICEF