# 1. WG - Archives & Records Management: [Cover]

| Deliverables as of April 2000 [basis for possible projects 20001-2003] | Target Date | Implementation Status Oct 2000 | New WG-ARM Deliverables as of Oct 2000 | Estimate Cost to expedite Special projects | New Target Date |
| --- | --- | --- | --- | --- | --- |
| 1. [prerequisite 2001] Some use of UN Archives as Common Depository for Core Records | Oct 2000 | UN/ARMS, including UNICEF and UNFPA core records, relocated to new sites. CS-ARC concept presented to CSTF. | CSTF approval for and establishment of CS-ARC |  | Dec 2000 to May 2001 |
| 1.a . Common Service Archive Research Centre [CS-ARC] | Nov 2000 | CSTF to comment on extent of support for CS-ARC and related consultancies | 2001 Project 1 Consultant[s] required [details below] procedures for retrievals, public access, generic service agreement, on-line access projects |  | Mar 2001 to Jan 2003 |
| 2. Harmonization of Archives and Records policies and procedures. Joint agency “electronic clearing House” | Mid 2000 | Ongoing – funding for special project on hold. Main task identified in Project proposal CS/TF to give guidance at Oct/Dec meeting | 2001 Project II Oct presentation/Dec deliberations Follow up with detailed proposal by April 2001 See details below |  | Apr 2001 to Feb 2003 |
| 3. Appraisal Decision Assistance | 2001 | 3 Phases identified Present to CS task force, Implement based on TF guidance and resource availability | 2001 Project III Based on feedback revise proposal with more detail presentation by June 2001 [see details below] |  | June 2001-Feb 2003 |
| 4. Digital Archives Study, Phase one Review. Security of electronic records for 2001-2003 | End 2000 | Presentation to CS TF and full consideration in 2001. Members to comment on study directions for CS approach | 2001 Project IV present outline to CS Task force on common strategy for long-term protection and accessibility of Electronic Records [see details below]s |  | Oct 2000 – Dec 2003 |
| 5. Record Series defined. Further clarification on some record series. | Feb 2001 | To be reconsidered by WG-ARM end 2001. | On hold Depends on broader appraisal Project. Goal for common series eg personnel or pension |  |  |
| 6. Working relationship with ISCC (+SIGs) to be regularized | Dec 2000 | On hold Proposals of SIG DAS etc | On hold : pending ISCC clarification and other NY priorities |  |  |
| 7. Explore External funding options for WG/Arm identified 19 related functions and Services | 2001 | Guidelines required on “external” funding issues. agreement on Functional areas and partner organizations | On hold survey 19 functions and services each org, prioritize “gap” projects , consultant, agreements |  |  |
| 8. Review special projects All previously proposed in light of funding | 2000 | Some projects discussed Oct 2000 Remainder to be considered 2001-2003 | On hold: Field Advice, .Declassification, Alternate Media, Doc Series Register, Global Files, Artifacts, Awards & Gifts to organizations |  |  |
| 9. Additional Items suggested by CS TF |  |  | On hold |  |  |