# 1. WG - Archives & Records Management: [Cover]

| Deliverables as of Oct 2000 [basis for possible projects 20001-2003] | Target Date | Implementation Status Apr 2001 | New WG-ARM Deliverables as of Apr 2001 | Estimate Cost to expedite Special projects | New Target Date |
| --- | --- | --- | --- | --- | --- |
| 1. Appraisal Decision Assistance | Dec 2001 | 3 Phases discussed by CS task Force, Consultant funding approved; TOR for Consultant for Phase 1 submitted to Procurement. .[see details previously provided] Implementation in each PA will be based on TF guidance and resource availability | 2001 Project I Based on feedback from PAs and international standards , consultant provides lists of appraisal Rules, links to lists of common & special PA record series etc. and recommends decision assistant tool. |  | Phase 1 = June 2001-Feb 2002 |
| 2. Digital Archives Study, Phase one Review. Security of electronic records for 2001-2003 | Dec 2001 | Presented to CS TF. Consultant funding approved for revision of 1998 report based on Participating NY agencies full involvement commenting on the draft etc. Consultants TOR submitted to Procurement,.. Records [see details previously provided] | 2001 Project II after consultants update of 1998 report, present outline to CS Task force of next phases on common strategy for long-term protection and accessibility of Electronic s |  | Phase 1 Aug 2001 – Mar 2002 |
| 3. Harmonization of Archives and Records policies and procedures. Joint agency “electronic clearing House” | Mid 2002 | Ongoing – funding for special project on hold. Main task identified in Project proposal CS/TF to give guidance at Oct/Dec meeting | 2002 Project I Represent to Task Force Dec 2001, See details previously provided |  | Apr 2002 to Feb 2003 |
| 4. Some use of UN Archives as Common Depository for Core Records | Oct 2000 | UN/ARMS, including UNICEF and UNFPA core records, relocated to new sites. CS-ARC concept presented to CSTF. Maintaining agreed limited growth with UNICEF and UNFPA only. | Present status of use to CSTF and obtain approval for expansion of service to other PAs and establishment of CS-ARC | Further development on hold see 2002 project | Dec 2001 to May 2002 |
| 4.a . Common Service Archive Research Centre [CS-ARC] | Dec 2001 | CSTF and NY PA’s to comment on extent of support for CS-ARC full establishment and related consultancies after completion of 2001 priority projects. Multi-Year Phased project to be proposed | 2002 Project 2 Consultant[s] required [details previously provided] procedures for retrievals, public access, generic service agreement, on-line access or digital conversion projects |  | Mar 2002 to Jun 2003 |
| 5. Record Series defined. Further clarification on some record series. | Feb 2002 | To be reconsidered by WG-ARM mid 2001. | On hold Depends on broader appraisal Project. Goal for common series eg personnel or pension |  |  |
| 6. Working relationship with ISCC (+SIGs) to be regularized | Dec 2001 | On hold Proposals of SIG DAS etc | On hold : pending ISCC clarification and other NY priorities |  |  |
| 7. Explore External funding options for WG/Arm identified 19 related functions and Services | 2002 | Guidelines required on “external” funding issues. agreement on Functional areas and partner organizations | On hold survey 19 functions and services each org, prioritize “gap” projects , consultant, agreements |  |  |
| 8. Review special projects All previously proposed in light of funding | 2002 | Some projects discussed Oct 2000 Remainder to be considered 2002-2003 | On hold: Field Advice, .Declassification, Alternate Media, Doc Series Register, Global Files, Artifacts, Awards & Gifts to organizations |  |  |
| 9. Additional Items suggested by CS TF |  |  | On hold |  |  |