Action Plan for initiating DAP project

|  | Activity | Deliverable | Responsible Party | Remarks | Time | Schedule |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Finalize EOI and submit to UN Procurement | EOI | PM | Reviewed and Approved by WGARM |  | 24 Sept |
| 2 | UN Procurement to review and post | EOI on Website | UN Proc | WGARM may also circulate EOI pointing to Website | 4 weeks | 25 Sept – 25 Oct |
| 3 | Update draft RFI and submit to UN Proc | Draft RFI | PM | Reviewed and approved by WGARM members | 1 week | 25 Sept – 2 Oct |
| 4 | UN Procurement to review and finalize RFI | Finalize RFI | UN Proc | UN Procurement will distribute RFI to interested vendors | 4 weeks | 3 – 25 Oct |
| 5 | Review and evaluate responses to RFI | Shortlist | PM/WGARM/UNProc | Establish review committee, review responses and shortlist | 2 weeks | 26 Oct – 14 Nov |
| 6 | Update SOW and submit to UN PROC | Final TOR/SOW | PM | Reviewed and approved by WGARM members | 1 week | 15 – 22 Nov |
| 7 | Finalize RFP | RFP | UN Proc/ UN Legal | Procurement and Legal activities | 2weeks | 25 Nov – 6 Dec |
| 8 | Send out RFP | Issue RFP | UN Proc | 5 week cut off for shortlisted vendors | 5 weeks | 9 Dec – 14 Jan |
| 9 | Review, evaluate RFP responses | Vendor Selection | PM/WGARM/UNProc | Establish review committee | 2 weeks | 15 – 25 Jan |
| 10 | Make recommendation | Submit | PM/UN Proc | UN Procurement activities | 1 week | 28 Jan – 1 Feb |
| 11 | Negotiate contract | Contract | UN legal | UN Legal activities | 3 weeks | 4 – 22 Feb |
| 12 | Project start up |  |  |  |  | 1 March |